## Instructions
ScaffSkills Project Cost Tracker
Module 6: Project Controls — Contract Management for Scaffolders
How to use this tracker:
• Enter project details in Sheet 2 — project name, contract value, client, dates, and labour rates.
• Update weekly every Friday with your labour hours, material costs, and plant & transport expenses.
• Enter the actual % complete honestly — this drives earned value calculations.
• The tracker calculates earned value and cost variance automatically. Monitor these for early warning signs.
• Share the 'Forecast Final Cost' with your weekly report to your project manager.
Colour Key:
Blue cells (like this) | Enter data here
White cells with formulas | Calculated automatically. Do not edit formula cells.

## Project Cost Tracker
SCAFFSKILLS
PROJECT COST TRACKER
Project Name: |  |  | Contract Value (£):
Client / Main Contractor: |  |  | Start Date:
Labour Rate (£/hr): | 28 |  | Budget — Labour (£):
Budget — Materials (£): |  |  | Budget — Plant & Transport (£):
TOTAL BUDGET (£): | 0
LIVE PROJECT SUMMARY
Total Spent to Date (£): | 0 |  | Earned Value to Date (£): | 0
Cost Variance (£): | 0 |  | Forecast Final Cost (£):
Forecast Margin (£): |  |  | Forecast Margin (%): | 0%
Week No. | Week Ending | Labour Hours | Labour Cost (£) | Materials (£) | Plant & Transport (£) | This Week Total (£) | Cumulative Cost (£) | % Complete | Earned Value (£) | Cost Variance (£) | Cost to Complete (£) | Forecast Final Cost (£) | Forecast Margin (£) | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40